## ProjectMonitoring
Programme | Batch (Start Yr - End Yr) | 2022-2026 | Project: | A GNN-Based Approach for Fraud Detection in Graphical Networks
| Group | 14 | Names: | Arnab Chattopadhyay, Abhirup Bag, Abhrajit Rath, Dhruba Dey
Attendance (Insert below names)
Date | Project discussions |  |  |  | Semester | Deliverable | Issues | Guide's remark | Arnab Chattopadhyay | Abhirup Bag | Abhrajit Rath | Dhruba Dey
2026-01-10 | Review of 7th sem work & improvement planning |  |  |  | 8 |  | Need to upgrade model performance | Focus on result improvement and evaluation | Present | Present | Present | Present
2026-01-17 | Advanced GNN concepts & GraphSAGE tuning |  |  |  | 8 |  | Hyperparameter confusion | Suggested tuning learning rate, layers | Present | absent | Present | Present
2026-01-24 | Dataset refinement & feature engineering |  |  |  | 8 |  | Feature redundancy | Remove noisy features, normalize data | Present | Present | Present | Present
2026-01-31 | Model re-training with optimized parameters |  |  |  | 8 |  | Overfitting observed | Apply dropout & regularization | Present | Present | Present | Present
2026-02-07 | Implementation of baseline ML models |  |  |  | 8 |  | Model comparison setup unclear | Implement LR, RF, GB for comparison | Present | Present | absent | Present
2026-02-14 | ROC–AUC evaluation & performance metrics |  |  |  | 8 | Performance Metrics | Metric interpretation issues | Focus on ROC curve analysis | Present | Present | Present | Present
2026-02-21 | Comparative result analysis |  |  |  | 8 |  | Result justification needed | Clearly explain why GNN outperforms | absent | Present | Present | Present
28-Feb-2026 | Visualization (graphs, ROC curves) |  |  |  | 8 |  | Graph plotting issues | Improve clarity of visual outputs | Present | Present | Present | Present
07-Mar-2026 | Testing and Result Analysis |  |  |  | 8 |  | Accuracy optimization and result interpretation | Recheck test accuracy and AUC | Present | Present | Present | absent
14-Mar-2026 | Prototype Development |  |  |  | 8 |  | Integration and performance issues | Guide reviewed the working prototype and suggested improvements in implementation and performance. | Present | Present | Present | Present
2026-03-21 | Prototype Testing and Validation |  |  |  | 8 | Validated Prototype | Minor bugs and result consistency | Guide evaluated prototype results and suggested minor corrections before final reporting. | Present | absent | Present | Present
28-Mar-2026 | Final Report Preparation |  |  |  | 8 | Final Report | Formatting and documentation improvements | Guide reviewed the draft final report and suggested formatting and documentation corrections. | Present | Present | Present | Present
02-Apr-2026 | Final Project Review |  |  |  | 8 |  | Minor corrections and formatting issues | Improve conclusion and future scope | Present | Present | Present | Present
4-Apr-2026 | Final Project Submission |  |  |  | 8 | Final Project Report | — | Project approved and submitted | Present | Present | Present | Present
Total | [8 empty] | 92.86% | 85.71% | 92.86% | 92.86%
Overall | [8 empty] | 92.86% | 85.71% | 92.86% | 92.86%
Guide's signature:
(Needed on hard-copy)

## Questions (hidden)
Area | Question | Raised By | Status (Open / Closed) | Response | Response By